## Summary
MDU Stage Cleanup — Team Review
Compiled during stage-by-stage cleanup of MDU pipeline (post 2026-04-29 restructure).
Each row in Review Items is an Opp where the current stage placement needs the owner to confirm or correct.
Pivot 1 — Items by Stage × Owner
Stage | Brett Spivey | Brett Spivey + Melissa Baker | Chuck McNeely (inactive) | Jeff Chao | Justin Barry | Melissa Baker | Tanya Friese | Taylor Mauney | Total
Engaged |  |  |  |  | 3 |  |  |  | 3
Contract Negotiations | 2 |  | 4 | 2 |  | 1 | 1 |  | 10
PAL/ROE Complete | 1 | 1 | 1 |  | 6 | 7 | 3 |  | 19
EMA/Bulk In Progress | 31 | [7 empty] | 31
EMA/Bulk Complete |  |  | 3 | [5 empty] | 3
On Hold | 1 |  |  |  |  | 1 |  | 1 | 3
TOTAL | 35 | 1 | 8 | 2 | 9 | 9 | 4 | 1 | 69
Pivot 2 — Items by Stage × IronClad linkage
Stage | IC Linked | Partial | No IC link | N/A | Total
Engaged |  |  | 3 |  | 3
Contract Negotiations |  |  | 10 |  | 10
PAL/ROE Complete |  | 2 | 8 | 9 | 19
EMA/Bulk In Progress |  |  | 31 |  | 31
EMA/Bulk Complete |  | 3 |  |  | 3
On Hold | 1 | 1 | 1 |  | 3

## Review Items
Stage | Owner | Opp Name | SF Id | IC Linked | IronClad IDs | Current State | Action Required | Decision | Notes
Contract Negotiations | Brett Spivey | Biltmore Terrace Condominiums | 006WR00000wj8KSYAY | No (0 of 1) |  | PAL Paused (manual SF entry, no IronClad). No Next_Action, no Projected. | Still in Contract Negotiations? Set Next_Action / Projected, or move to On Hold.
Contract Negotiations | Brett Spivey | Diamond Fork Apartments | 006WR00000wkAW3YAM | No (0 of 1) |  | PAL Paused (manual). No Next_Action, no Projected. | Still in negotiations or On Hold?
EMA/Bulk In Progress | Brett Spivey | Woodland Trio The Oaks | 006WR00000wkEaQYAU | No (0 of 3) |  | Woodland Trio The Oaks. PAL Completed (signed 2023-11-01 — bulk import date). EMA=AGR-0790 Review, Bulk=AGR-0791 Review (manual, no IronClad). ST=P-003339 at "Project - PAL/ROE Signed" (no construction). No Next_Action / Projected. | (A) IN NEGOTIATION — keep here, set Next_Action + Projected. (B) NOT NEGOTIATING — drop to PAL/ROE Complete, cancel placeholder EMA + Bulk. (C) OTHER — explain.
EMA/Bulk In Progress | Brett Spivey | Baldwin Manor | 006WR00000wkEaRYAU | No (0 of 3) |  | Baldwin Manor. PAL Completed (signed 2023-11-01 — bulk import date). EMA=AGR-0793 Review, Bulk=AGR-0794 Review (manual, no IronClad). ST=P-003350 at "Project - PAL/ROE Signed" (no construction). No Next_Action / Projected. | (A) IN NEGOTIATION — keep here, set Next_Action + Projected. (B) NOT NEGOTIATING — drop to PAL/ROE Complete, cancel placeholder EMA + Bulk. (C) OTHER — explain.
EMA/Bulk In Progress | Brett Spivey | White Oak Terrace | 006WR00000wkEaSYAU | No (0 of 3) |  | White Oak Terrace. PAL Completed (signed 2023-11-01 — bulk import date). EMA=AGR-0796 Review, Bulk=AGR-0797 Review (manual, no IronClad). ST=P-003337 at "Project - PAL/ROE Signed" (no construction). No Next_Action / Projected. | (A) IN NEGOTIATION — keep here, set Next_Action + Projected. (B) NOT NEGOTIATING — drop to PAL/ROE Complete, cancel placeholder EMA + Bulk. (C) OTHER — explain.
EMA/Bulk In Progress | Brett Spivey | Bali Apartments | 006WR00000wkEaTYAU | No (0 of 3) |  | Bali Apartments. PAL Completed (signed 2023-11-01 — bulk import date). EMA=AGR-0799 Review, Bulk=AGR-0800 Review (manual, no IronClad). ST=P-003352 at "Project - PAL/ROE Signed" (no construction). No Next_Action / Projected. | (A) IN NEGOTIATION — keep here, set Next_Action + Projected. (B) NOT NEGOTIATING — drop to PAL/ROE Complete, cancel placeholder EMA + Bulk. (C) OTHER — explain.
EMA/Bulk In Progress | Brett Spivey | Corbett Avenue Apartments | 006WR00000wkEaUYAU | No (0 of 3) |  | Corbett Avenue Apartments. PAL Completed (signed 2023-11-01 — bulk import date). EMA=AGR-0802 Review, Bulk=AGR-0803 Review (manual, no IronClad). ST=P-003383 at "Project - PAL/ROE Signed" (no construction). No Next_Action / Projected. | (A) IN NEGOTIATION — keep here, set Next_Action + Projected. (B) NOT NEGOTIATING — drop to PAL/ROE Complete, cancel placeholder EMA + Bulk. (C) OTHER — explain.
EMA/Bulk In Progress | Brett Spivey | Chatsworth Plaza | 006WR00000wkEaVYAU | No (0 of 3) |  | Chatsworth Plaza. PAL Completed (signed 2023-11-01 — bulk import date). EMA=AGR-0805 Review, Bulk=AGR-0806 Review (manual, no IronClad). ST=P-003345 at "Project - PAL/ROE Signed" (no construction). No Next_Action / Projected. | (A) IN NEGOTIATION — keep here, set Next_Action + Projected. (B) NOT NEGOTIATING — drop to PAL/ROE Complete, cancel placeholder EMA + Bulk. (C) OTHER — explain.
EMA/Bulk In Progress | Brett Spivey | John Manor | 006WR00000wkEaWYAU | No (0 of 3) |  | John Manor. PAL Completed (signed 2023-11-01 — bulk import date). EMA=AGR-0808 Review, Bulk=AGR-0809 Review (manual, no IronClad). ST=P-003384 at "Project - PAL/ROE Signed" (no construction). No Next_Action / Projected. | (A) IN NEGOTIATION — keep here, set Next_Action + Projected. (B) NOT NEGOTIATING — drop to PAL/ROE Complete, cancel placeholder EMA + Bulk. (C) OTHER — explain.
EMA/Bulk In Progress | Brett Spivey | Casa Linda | 006WR00000wkEaXYAU | No (0 of 3) |  | Casa Linda. PAL Completed (signed 2023-11-01 — bulk import date). EMA=AGR-0811 Review, Bulk=AGR-0812 Review (manual, no IronClad). ST=P-003347 at "Project - PAL/ROE Signed" (no construction). No Next_Action / Projected. | (A) IN NEGOTIATION — keep here, set Next_Action + Projected. (B) NOT NEGOTIATING — drop to PAL/ROE Complete, cancel placeholder EMA + Bulk. (C) OTHER — explain.
EMA/Bulk In Progress | Brett Spivey | Windsor Manor | 006WR00000wkEaYYAU | No (0 of 3) |  | Windsor Manor. PAL Completed (signed 2023-11-01 — bulk import date). EMA=AGR-0814 Review, Bulk=AGR-0815 Review (manual, no IronClad). ST=P-003381 at "Project - PAL/ROE Signed" (no construction). No Next_Action / Projected. | (A) IN NEGOTIATION — keep here, set Next_Action + Projected. (B) NOT NEGOTIATING — drop to PAL/ROE Complete, cancel placeholder EMA + Bulk. (C) OTHER — explain.
EMA/Bulk In Progress | Brett Spivey | Coliseum Apartments | 006WR00000wkEaZYAU | No (0 of 3) |  | Coliseum Apartments. PAL Completed (signed 2023-11-01 — bulk import date). EMA=AGR-0817 Review, Bulk=AGR-0818 Review (manual, no IronClad). ST=P-003343 at "Project - PAL/ROE Signed" (no construction). No Next_Action / Projected. | (A) IN NEGOTIATION — keep here, set Next_Action + Projected. (B) NOT NEGOTIATING — drop to PAL/ROE Complete, cancel placeholder EMA + Bulk. (C) OTHER — explain.
EMA/Bulk In Progress | Brett Spivey | Colonial Manor Apartments | 006WR00000wkEaaYAE | No (0 of 3) |  | Colonial Manor Apartments. PAL Completed (signed 2023-11-01 — bulk import date). EMA=AGR-0820 Review, Bulk=AGR-0821 Review (manual, no IronClad). ST=P-003342 at "Project - PAL/ROE Signed" (no construction). No Next_Action / Projected. | (A) IN NEGOTIATION — keep here, set Next_Action + Projected. (B) NOT NEGOTIATING — drop to PAL/ROE Complete, cancel placeholder EMA + Bulk. (C) OTHER — explain.
EMA/Bulk In Progress | Brett Spivey | San Vicente Apartments | 006WR00000wkEabYAE | No (0 of 3) |  | San Vicente Apartments. PAL Completed (signed 2023-11-01 — bulk import date). EMA=AGR-0823 Review, Bulk=AGR-0824 Review (manual, no IronClad). ST=P-003385 at "Project - PAL/ROE Signed" (no construction). No Next_Action / Projected. | (A) IN NEGOTIATION — keep here, set Next_Action + Projected. (B) NOT NEGOTIATING — drop to PAL/ROE Complete, cancel placeholder EMA + Bulk. (C) OTHER — explain.
EMA/Bulk In Progress | Brett Spivey | St. Andrews Manor | 006WR00000wkEacYAE | No (0 of 3) |  | St. Andrews Manor. PAL Completed (signed 2023-11-01 — bulk import date). EMA=AGR-0826 Review, Bulk=AGR-0827 Review (manual, no IronClad). ST=P-003386 at "Project - PAL/ROE Signed" (no construction). No Next_Action / Projected. | (A) IN NEGOTIATION — keep here, set Next_Action + Projected. (B) NOT NEGOTIATING — drop to PAL/ROE Complete, cancel placeholder EMA + Bulk. (C) OTHER — explain.
EMA/Bulk In Progress | Brett Spivey | Krystal Terrace | 006WR00000wkEadYAE | No (0 of 3) |  | Krystal Terrace. PAL Completed (signed 2023-11-01 — bulk import date). EMA=AGR-0829 Review, Bulk=AGR-0830 Review (manual, no IronClad). ST=P-003387 at "Project - PAL/ROE Signed" (no construction). No Next_Action / Projected. | (A) IN NEGOTIATION — keep here, set Next_Action + Projected. (B) NOT NEGOTIATING — drop to PAL/ROE Complete, cancel placeholder EMA + Bulk. (C) OTHER — explain.
EMA/Bulk In Progress | Brett Spivey | Parkway Terrace | 006WR00000wkEaeYAE | No (0 of 3) |  | Parkway Terrace. PAL Completed (signed 2023-11-01 — bulk import date). EMA=AGR-0832 Review, Bulk=AGR-0833 Review (manual, no IronClad). ST=P-003388 at "Project - PAL/ROE Signed" (no construction). No Next_Action / Projected. | (A) IN NEGOTIATION — keep here, set Next_Action + Projected. (B) NOT NEGOTIATING — drop to PAL/ROE Complete, cancel placeholder EMA + Bulk. (C) OTHER — explain.
EMA/Bulk In Progress | Brett Spivey | Kling Trio Apartments | 006WR00000wkEafYAE | No (0 of 3) |  | Kling Trio Apartments. PAL Completed (signed 2023-11-01 — bulk import date). EMA=AGR-0835 Review, Bulk=AGR-0836 Review (manual, no IronClad). ST=P-003336 at "Project - PAL/ROE Signed" (no construction). No Next_Action / Projected. | (A) IN NEGOTIATION — keep here, set Next_Action + Projected. (B) NOT NEGOTIATING — drop to PAL/ROE Complete, cancel placeholder EMA + Bulk. (C) OTHER — explain.
EMA/Bulk In Progress | Brett Spivey | Jaclyn Terrace | 006WR00000wkEagYAE | No (0 of 3) |  | Jaclyn Terrace. PAL Completed (signed 2023-11-01 — bulk import date). EMA=AGR-0838 Review, Bulk=AGR-0839 Review (manual, no IronClad). ST=P-003338 at "Project - PAL/ROE Signed" (no construction). No Next_Action / Projected. | (A) IN NEGOTIATION — keep here, set Next_Action + Projected. (B) NOT NEGOTIATING — drop to PAL/ROE Complete, cancel placeholder EMA + Bulk. (C) OTHER — explain.
EMA/Bulk In Progress | Brett Spivey | Brody Terrace (Riverside) | 006WR00000wkEahYAE | No (0 of 3) |  | Brody Terrace (Riverside). PAL Completed (signed 2023-11-01 — bulk import date). EMA=AGR-0841 Review, Bulk=AGR-0842 Review (manual, no IronClad). ST=P-003331 at "Project - PAL/ROE Signed" (no construction). No Next_Action / Projected. | (A) IN NEGOTIATION — keep here, set Next_Action + Projected. (B) NOT NEGOTIATING — drop to PAL/ROE Complete, cancel placeholder EMA + Bulk. (C) OTHER — explain.
EMA/Bulk In Progress | Brett Spivey | Parkview Terrace | 006WR00000wkEaiYAE | No (0 of 3) |  | Parkview Terrace. PAL Completed (signed 2023-11-01 — bulk import date). EMA=AGR-0844 Review, Bulk=AGR-0845 Review (manual, no IronClad). ST=P-003334 at "Project - PAL/ROE Signed" (no construction). No Next_Action / Projected. | (A) IN NEGOTIATION — keep here, set Next_Action + Projected. (B) NOT NEGOTIATING — drop to PAL/ROE Complete, cancel placeholder EMA + Bulk. (C) OTHER — explain.
EMA/Bulk In Progress | Brett Spivey | Roxanne Apartments | 006WR00000wkEajYAE | No (0 of 3) |  | Roxanne Apartments. PAL Completed (signed 2023-11-01 — bulk import date). EMA=AGR-0847 Review, Bulk=AGR-0848 Review (manual, no IronClad). ST=P-003353 at "Project - PAL/ROE Signed" (no construction). No Next_Action / Projected. | (A) IN NEGOTIATION — keep here, set Next_Action + Projected. (B) NOT NEGOTIATING — drop to PAL/ROE Complete, cancel placeholder EMA + Bulk. (C) OTHER — explain.
EMA/Bulk In Progress | Brett Spivey | Riverside Villa Apartments | 006WR00000wkEakYAE | No (0 of 3) |  | Riverside Villa Apartments. PAL Completed (signed 2023-11-01 — bulk import date). EMA=AGR-0850 Review, Bulk=AGR-0851 Review (manual, no IronClad). ST=P-003330 at "Project - PAL/ROE Signed" (no construction). No Next_Action / Projected. | (A) IN NEGOTIATION — keep here, set Next_Action + Projected. (B) NOT NEGOTIATING — drop to PAL/ROE Complete, cancel placeholder EMA + Bulk. (C) OTHER — explain.
EMA/Bulk In Progress | Brett Spivey | The Banyans | 006WR00000wkEalYAE | No (0 of 3) |  | The Banyans. PAL Completed (signed 2023-11-01 — bulk import date). EMA=AGR-0853 Review, Bulk=AGR-0854 Review (manual, no IronClad). ST=P-003351 at "Project - PAL/ROE Signed" (no construction). No Next_Action / Projected. | (A) IN NEGOTIATION — keep here, set Next_Action + Projected. (B) NOT NEGOTIATING — drop to PAL/ROE Complete, cancel placeholder EMA + Bulk. (C) OTHER — explain.
EMA/Bulk In Progress | Brett Spivey | Topanga Apartments | 006WR00000wkEamYAE | No (0 of 3) |  | Topanga Apartments. PAL Completed (signed 2023-11-01 — bulk import date). EMA=AGR-0856 Review, Bulk=AGR-0857 Review (manual, no IronClad). ST=P-003344 at "Project - PAL/ROE Signed" (no construction). No Next_Action / Projected. | (A) IN NEGOTIATION — keep here, set Next_Action + Projected. (B) NOT NEGOTIATING — drop to PAL/ROE Complete, cancel placeholder EMA + Bulk. (C) OTHER — explain.
EMA/Bulk In Progress | Brett Spivey | Topanga Terrace | 006WR00000wkEanYAE | No (0 of 3) |  | Topanga Terrace. PAL Completed (signed 2023-11-01 — bulk import date). EMA=AGR-0859 Review, Bulk=AGR-0860 Review (manual, no IronClad). ST=P-003341 at "Project - PAL/ROE Signed" (no construction). No Next_Action / Projected. | (A) IN NEGOTIATION — keep here, set Next_Action + Projected. (B) NOT NEGOTIATING — drop to PAL/ROE Complete, cancel placeholder EMA + Bulk. (C) OTHER — explain.
EMA/Bulk In Progress | Brett Spivey | Vista Apartments | 006WR00000wkEaoYAE | No (0 of 3) |  | Vista Apartments. PAL Completed (signed 2023-11-01 — bulk import date). EMA=AGR-0862 Review, Bulk=AGR-0863 Review (manual, no IronClad). ST=P-003340 at "Project - PAL/ROE Signed" (no construction). No Next_Action / Projected. | (A) IN NEGOTIATION — keep here, set Next_Action + Projected. (B) NOT NEGOTIATING — drop to PAL/ROE Complete, cancel placeholder EMA + Bulk. (C) OTHER — explain.
EMA/Bulk In Progress | Brett Spivey | The Palms | 006WR00000wkEapYAE | No (0 of 3) |  | The Palms. PAL Completed (signed 2023-11-01 — bulk import date). EMA=AGR-0865 Review, Bulk=AGR-0866 Review (manual, no IronClad). ST=P-003346 at "Project - PAL/ROE Signed" (no construction). No Next_Action / Projected. | (A) IN NEGOTIATION — keep here, set Next_Action + Projected. (B) NOT NEGOTIATING — drop to PAL/ROE Complete, cancel placeholder EMA + Bulk. (C) OTHER — explain.
EMA/Bulk In Progress | Brett Spivey | First Casa De Marina | 006WR00000wkEbIYAU | No (0 of 3) |  | First Casa De Marina. PAL Completed (signed 2023-11-01 — bulk import date). EMA=AGR-0926 Review, Bulk=AGR-0927 Review (manual, no IronClad). ST=P-003281 at "Project - PAL/ROE Signed" (no construction). No Next_Action / Projected. | (A) IN NEGOTIATION — keep here, set Next_Action + Projected. (B) NOT NEGOTIATING — drop to PAL/ROE Complete, cancel placeholder EMA + Bulk. (C) OTHER — explain.
EMA/Bulk In Progress | Brett Spivey | Lombardi Apartments | 006WR00000wkEbJYAU | No (0 of 3) |  | Lombardi Apartments. PAL Completed (signed 2023-11-01 — bulk import date). EMA=AGR-0929 Review, Bulk=AGR-0930 Review (manual, no IronClad). ST=P-003335 at "Project - PAL/ROE Signed" (no construction). No Next_Action / Projected. | (A) IN NEGOTIATION — keep here, set Next_Action + Projected. (B) NOT NEGOTIATING — drop to PAL/ROE Complete, cancel placeholder EMA + Bulk. (C) OTHER — explain.
EMA/Bulk In Progress | Brett Spivey | The Meadows at Westlake Village | 006WR00000wkEbKYAU | No (0 of 3) |  | The Meadows at Westlake Village. PAL Completed (signed 2023-11-01 — bulk import date). EMA=AGR-0932 Review, Bulk=AGR-0933 Review (manual, no IronClad). ST=P-003348 at "Project - PAL/ROE Signed" (no construction). No Next_Action / Projected. | (A) IN NEGOTIATION — keep here, set Next_Action + Projected. (B) NOT NEGOTIATING — drop to PAL/ROE Complete, cancel placeholder EMA + Bulk. (C) OTHER — explain.
EMA/Bulk In Progress | Brett Spivey | Brookside Terrace Apartments | 006WR00000wkEbLYAU | No (0 of 3) |  | Brookside Terrace Apartments. PAL Completed (signed 2023-11-01 — bulk import date). EMA=AGR-0935 Review, Bulk=AGR-0936 Review (manual, no IronClad). ST=P-003349 at "Project - PAL/ROE Signed" (no construction). No Next_Action / Projected. | (A) IN NEGOTIATION — keep here, set Next_Action + Projected. (B) NOT NEGOTIATING — drop to PAL/ROE Complete, cancel placeholder EMA + Bulk. (C) OTHER — explain.
EMA/Bulk In Progress | Brett Spivey | Parthenia Terrace | 006WR00000wkEbNYAU | No (0 of 3) |  | Parthenia Terrace. PAL Completed (signed 2023-11-01 — bulk import date). EMA=AGR-0941 Review, Bulk=AGR-0942 Review (manual, no IronClad). ST=P-003332 at "Project - PAL/ROE Signed" (no construction). No Next_Action / Projected. | (A) IN NEGOTIATION — keep here, set Next_Action + Projected. (B) NOT NEGOTIATING — drop to PAL/ROE Complete, cancel placeholder EMA + Bulk. (C) OTHER — explain.
On Hold | Brett Spivey | The Traditions Apartments | 006WR00000wkEbvYAE | Partial (1 of 4) | AGR-1021 PAL=IC-171 | Next_Action: "Niraj sending legal note to Caitlin re cancellation comm to owner; PAL not being" | Cancellation in progress — should this close out as Closed Lost rather than sit On Hold?
PAL/ROE Complete | Brett Spivey | Capri on Camelback | 006WR00000wkEc3YAE | Partial (1 of 3) | AGR-1039 PAL=IC-153 | Bulk AGR-1040 Status=Completed but Signed_Date=None and no IronClad. Next_Action says "Brett to contact owner re bulk requirement". | Either Bulk really is Completed (fill Signed_Date + IronClad link) or Status is wrong.
PAL/ROE Complete | Brett Spivey + Melissa Baker | Converge Justin | 006WR00000yvY5dYAE | No Agreements |  | Possible duplicate. Both empty Converge Justin records. Brett=PAL/ROE Complete, Melissa=CN (006WR000011cV9lYAE). | Pick one to keep, close the other.
Contract Negotiations | Chuck McNeely (inactive) | Kirshenbaum Apartments | 006WR00000wk9S0YAI | No (0 of 1) |  | PAL Review (manual). | Reassign owner. Verify stage.
Contract Negotiations | Chuck McNeely (inactive) | Temple Square Apts | 006WR00000wk9S5YAI | No (0 of 2) |  | PAL+EMA Paused (manual). | Reassign owner. Likely On Hold.
Contract Negotiations | Chuck McNeely (inactive) | Chalet Apartments | 006WR00000wk9SjYAI | No (0 of 2) |  | PAL Review + ROE Cancelled (manual). | Reassign owner. Verify Contract Negotiations is correct.
Contract Negotiations | Chuck McNeely (inactive) | Spindrift Del Mar HOA | 006WR00000wk9SwYAI | No (0 of 1) |  | PAL Paused (manual). | Reassign owner. Likely On Hold given Paused agreement + zero recent signals.
EMA/Bulk Complete | Chuck McNeely (inactive) | The Renaissance at Stoney Creek | 006WR00000wk1EjYAI | Partial (1 of 3) | AGR-1291 PAL=IC-1504 | The Renaissance at Stoney Creek. PAL AGR-1291 Completed (IC-1504), EMA AGR-1292 Archive (never signed), PAL Addendum AGR-1293 Completed. ST P-006296 Build Completed. | (A) MOVE TO PAL/ROE COMPLETE — EMA never signed (Archive correct). (B) STAY HERE — EMA actually signed, fix Status + Signed_Date. PLUS reassign owner.
EMA/Bulk Complete | Chuck McNeely (inactive) | The Bluffs of Brookside | 006WR00000wk1ElYAI | Partial (1 of 3) | AGR-1298 PAL=IC-1499 | The Bluffs of Brookside. PAL AGR-1298 Completed (IC-1499), EMA AGR-1299 Archive (never signed), PAL Addendum AGR-1300 Completed. ST P-006292 Build Completed. | (A) MOVE TO PAL/ROE COMPLETE — EMA never signed (Archive correct). (B) STAY HERE — EMA actually signed, fix Status + Signed_Date. PLUS reassign owner.
EMA/Bulk Complete | Chuck McNeely (inactive) | Arbors of Killeen | 006WR00000wkEcmYAE | Partial (1 of 3) | AGR-1165 PAL=IC-1084 | Arbors of Killeen. PAL AGR-1165 Completed (IC-1084), EMA AGR-1166 Archive (never signed), PAL Addendum AGR-1167 Completed. ST P-004231 Build Completed. | (A) MOVE TO PAL/ROE COMPLETE — EMA never signed (Archive correct). (B) STAY HERE — EMA actually signed, fix Status + Signed_Date. PLUS reassign owner.
PAL/ROE Complete | Chuck McNeely (inactive) | Lexington Place (Monterey) | 006WR00000wkEcKYAU | No Agreements |  | Lexington Place (Monterey). No Agreement, no Next_Action, no Projected, owner inactive. | Reassign + verify stage.
Contract Negotiations | Jeff Chao | The Upland | 006WR00000wjnlUYAQ | No (0 of 2) |  | PAL Paused + EMA Review (manual). No Next_Action, no Projected, no IronClad. | Still alive or On Hold?
Contract Negotiations | Jeff Chao | University Apartments | 006WR00000wjnmKYAQ | No (0 of 2) |  | PAL Paused + EMA Completed signed 2025-01-21 (manual, no IronClad backing). | EMA shows Completed/signed 1/21/25 — if real, this is PAL/ROE Complete. Confirm: was EMA actually signed?
Engaged | Justin Barry | Bridgeport_MDU_Federal Housing Administration | 006WR00000xuFKAYA2 | No Agreements |  | Bridgeport_MDU_Federal Housing Administration. Moved into Engaged 2026-05-01. No Next_Action set. | Set Next_Action describing where this stands.
Engaged | Justin Barry | 1342 Eolus Ave | 006WR00000yur0lYAA | No Agreements |  | 1/27 voicemail to Stephanie. Three prior calls, no callback. "10/10 pending contact from Mason." | Confirm still Engaged. If yes, set Next_Action. If unreachable, drop to Prospects or Closed Lost.
Engaged | Justin Barry | 978 Hygeia Ave | 006WR00000ywTYXYA2 | No Agreements |  | 3/11 followup with Simon. 2/11 sent Easement Agreement. 1/27/26 completed easement. | Is Simon still moving? If yes, set Next_Action with target. If stalled, drop stage.
PAL/ROE Complete | Justin Barry | 512-514 Via De La Valle | (no SF Id — backfill) | N/A |  | 512-514 Via De La Valle — no PAL/ROE Agreement__c record. | Backfill PAL Agreement record, or accept the gap?
PAL/ROE Complete | Justin Barry | Solana Beach and Tennis Club | 006WR00000wk9YTYAY | Partial (1 of 2) | AGR-1442 ROE=IC-3296 | "Confirmed Ting bulk signed at this property per Dave Putnam" (10/4/24). No Bulk Agreement record exists. | Verify Bulk signed. Create Bulk Agreement__c record (auto-bumps to EMA/Bulk Complete) or confirm not active.
PAL/ROE Complete | Justin Barry | Green Valley Mobile Estates Encinitas | 006WR00000wkA6iYAE | No (0 of 1) |  | ROE AGR-1417 Status=Sign but Next_Action says "ROE signed - awaiting build orders". | Update Status to Completed + populate Signed_Date.
PAL/ROE Complete | Justin Barry | Del Mar Beach Club | 006WR00000wkClNYAU | No (0 of 1) |  | "Ting BULK Confirmed by SFU Team" (10/8/24). No Bulk Agreement record exists. | Verify Bulk signed. Create Bulk Agreement__c record or confirm not active.
PAL/ROE Complete | Justin Barry | Las Brisas | 006WR00000wkClkYAE | No (0 of 1) |  | "Ting Bulk confirmed by SFU Team" (10/8/24). No Bulk Agreement record exists. | Verify Bulk signed. Create Bulk Agreement__c record or confirm not active.
PAL/ROE Complete | Justin Barry | Del Mar Shores Terrace | 006WR00000wkCllYAE | No (0 of 1) |  | "Ting BULK Confirmed by SFU Team" (10/8/24). No Bulk Agreement record exists. | Verify Bulk signed. Create Bulk Agreement__c record or confirm not active.
Contract Negotiations | Melissa Baker | Converge Justin | 006WR000011cV9lYAE | No Agreements |  | NONE — empty record. Zero data: no agreements, no notes, no Next_Action, no Projected. | Was this created in error or as a placeholder? Delete or define purpose.
On Hold | Melissa Baker | Horizon Heights | 006WR00000wkEb1YAE | Yes | AGR-0894 PAL=IC-1772 | Next_Action: "Need Data and approval to walk [Placeholder forecast - update with real estimate", Projected=2026-07-27 | Active work + forecast date. Why On Hold rather than Engaged / Prospecting / Contract Negotiations?
PAL/ROE Complete | Melissa Baker | Decatur_MDU_Smallwood Trailer Park | (no SF Id — backfill) | N/A |  | Decatur_MDU_Smallwood Trailer Park — no PAL/ROE Agreement__c record (CX-tracking). | Backfill PAL Agreement record, or accept the gap?
PAL/ROE Complete | Melissa Baker | Omaha_MDU_4612 Redman Ave | (no SF Id — backfill) | N/A |  | Omaha_MDU_4612 Redman Ave — no PAL/ROE Agreement__c record. | Backfill PAL Agreement record, or accept the gap?
PAL/ROE Complete | Melissa Baker | Omaha_MDU_4760 LAFAYETTE AVE | (no SF Id — backfill) | N/A |  | Omaha_MDU_4760 LAFAYETTE AVE — no PAL/ROE Agreement__c record. | Backfill PAL Agreement record, or accept the gap?
PAL/ROE Complete | Melissa Baker | Omaha_MDU_5004 Davenport St | (no SF Id — backfill) | N/A |  | Omaha_MDU_5004 Davenport St — no PAL/ROE Agreement__c record. | Backfill PAL Agreement record, or accept the gap?
PAL/ROE Complete | Melissa Baker | Omaha_MDU_9208 Ohio St | (no SF Id — backfill) | N/A |  | Omaha_MDU_9208 Ohio St — no PAL/ROE Agreement__c record. | Backfill PAL Agreement record, or accept the gap?
PAL/ROE Complete | Melissa Baker | Omaha_MDU_Benson Crest Apartments 2 | (no SF Id — backfill) | N/A |  | Omaha_MDU_Benson Crest Apartments 2 — no PAL/ROE Agreement__c record. | Backfill PAL Agreement record, or accept the gap?
PAL/ROE Complete | Melissa Baker | Omaha_MDU_Farnam Flats | (no SF Id — backfill) | N/A |  | Omaha_MDU_Farnam Flats — no PAL/ROE Agreement__c record. | Backfill PAL Agreement record, or accept the gap?
Contract Negotiations | Tanya Friese | Taschner Apartments | 006WR00000wk9SGYAY | No (0 of 1) |  | PAL Review (manual). No Next_Action, no Projected, no IronClad. | Still active or On Hold?
PAL/ROE Complete | Tanya Friese | Paul Mark Apts | (no SF Id — backfill) | N/A |  | Paul Mark Apts — no PAL/ROE Agreement__c record. | Backfill PAL Agreement record, or accept the gap?
PAL/ROE Complete | Tanya Friese | 1507 N 8th Apartments_Colt RE | 006WR00000wkEbPYAU | No (0 of 1) |  | "PAL signed, waiting on PAL addendum and verbal on EMA" (4/24/26). | Is the EMA active enough to bump to EMA/Bulk In Progress, or stay in PAL/ROE Complete?
PAL/ROE Complete | Tanya Friese | Killeen_MDU_Bradley Arms | 006WR00000xuzoQYAQ | No Agreements |  | "verbal on EMA" (weekly tracker note). Possible dupe with Bradley Arms_Colt RE. | Confirm EMA status. Confirm dupe with Bradley Arms_Colt RE (006WR00000wkCjuYAE).
On Hold | Taylor Mauney | TEST PROPERTY 2 | 006WR0000112YsXYAU | No Agreements |  | Name="TEST PROPERTY 2", Projected=2026-07-31 | DELETE — test record in production pipeline.

## On Hold (all 282)
Owner | Opp Name | SF Id | Hold Reason | Last Activity | Bucket | Action Required | Decision
Bill Holick | Eagle's Point Apartments | 006WR00000wkCljYAE | Other | 2026-04-24 | dormant | — low priority — owner triage when Hold_Reason picklist is enriched.
Bill Holick | Evergreen At Keller | 006WR00000wjKFsYAM | Other | 2026-04-24 | dormant | — low priority — owner triage when Hold_Reason picklist is enriched.
Bill Holick | Lemon & Pear Tree Apartments | 006WR00000wkDLxYAM | Other | 2026-04-24 | dormant | — low priority — owner triage when Hold_Reason picklist is enriched.
Bill Holick | Martinique Apartments | 006WR00000wkDMTYA2 | Other | 2026-04-24 | dormant | — low priority — owner triage when Hold_Reason picklist is enriched.
Bill Holick | Pacific Villas | 006WR00000wkC7OYAU | Other | 2026-04-24 | dormant | — low priority — owner triage when Hold_Reason picklist is enriched.
Bill Holick | Solana Highlands | 006WR00000wk9YNYAY | Other | 2026-04-24 | dormant | — low priority — owner triage when Hold_Reason picklist is enriched.
Bill Holick | The Forum Apartments FKA Archstone Apartments | 006WR00000wkDM2YAM | Other | 2026-04-24 | dormant | — low priority — owner triage when Hold_Reason picklist is enriched.
Brett Spivey | 6311-6321 Roosevelt | 006WR00000wkDuNYAU | Other | 2026-04-24 | dormant | — low priority — owner triage when Hold_Reason picklist is enriched.
Brett Spivey | Arcadia Walk | 006WR00000wkEbHYAU | Other | 2026-04-24 | dormant | — low priority — owner triage when Hold_Reason picklist is enriched.
Brett Spivey | Bella Vita | 006WR00000wkACGYA2 | Other | 2026-04-24 | dormant | — low priority — owner triage when Hold_Reason picklist is enriched.
Brett Spivey | Chambers Creek Estates | 006WR00000wjdjuYAA | Other | 2026-04-24 | dormant | — low priority — owner triage when Hold_Reason picklist is enriched.
Brett Spivey | Cielo II Apartments | 006WR00000wkDu0YAE | Other | 2026-04-24 | dormant | — low priority — owner triage when Hold_Reason picklist is enriched.
Brett Spivey | Estates at Park Central | 006WR00000wkAkAYAU | Other | 2026-04-24 | dormant | — low priority — owner triage when Hold_Reason picklist is enriched.
Brett Spivey | Hunt Club Apartments | 006WR00000wjdjpYAA | Other | 2026-04-24 | dormant | — low priority — owner triage when Hold_Reason picklist is enriched.
Brett Spivey | Jasper Apartments | 006WR00000wkArfYAE | Other | 2026-04-24 | dormant | — low priority — owner triage when Hold_Reason picklist is enriched.
Brett Spivey | Kensington Apartments | 006WR00000wkA6xYAE | Other | 2026-04-24 | dormant | — low priority — owner triage when Hold_Reason picklist is enriched.
Brett Spivey | Maple Pointe Apartments | 006WR00000wkAW1YAM | Other | 2026-04-24 | dormant | — low priority — owner triage when Hold_Reason picklist is enriched.
Brett Spivey | Mariposa Apartments | 006WR00000wkDtmYAE | Other | 2026-04-24 | dormant | — low priority — owner triage when Hold_Reason picklist is enriched.
Brett Spivey | Maryland Lakes | 006WR00000wkACHYA2 | Other | 2026-04-24 | dormant | — low priority — owner triage when Hold_Reason picklist is enriched.
Brett Spivey | Meridian at the Hermitage | 006WR00000wkCl3YAE | Other | 2026-04-24 | dormant | — low priority — owner triage when Hold_Reason picklist is enriched.
Brett Spivey | Mezzo Condominiums | 006WR00000wkC78YAE | Other | 2026-04-24 | dormant | — low priority — owner triage when Hold_Reason picklist is enriched.
Brett Spivey | Olive East | 006WR00000wkDtxYAE | Other | 2026-04-24 | dormant | — low priority — owner triage when Hold_Reason picklist is enriched.
Brett Spivey | Palmero by the Park (f/k/a Overlook by the Park) | 006WR00000wkDu2YAE | Other | 2026-04-24 | dormant | — low priority — owner triage when Hold_Reason picklist is enriched.
Brett Spivey | Park Winds Apartments | 006WR00000wk9SIYAY | Other | 2026-04-24 | dormant | — low priority — owner triage when Hold_Reason picklist is enriched.
Brett Spivey | Pembrooke Apartments | 006WR00000wkAVyYAM | Other | 2026-04-24 | dormant | — low priority — owner triage when Hold_Reason picklist is enriched.
Brett Spivey | Prairie Winds Apartments | 006WR00000wk9SJYAY | Other | 2026-04-24 | dormant | — low priority — owner triage when Hold_Reason picklist is enriched.
Brett Spivey | Riverwood Apartments | 006WR00000wkAVuYAM | Other | 2026-04-24 | dormant | — low priority — owner triage when Hold_Reason picklist is enriched.
Brett Spivey | Sahara & Playa Palms Apartments | 006WR00000wkEbGYAU | Other | 2026-04-24 | dormant | — low priority — owner triage when Hold_Reason picklist is enriched.
Brett Spivey | San Angelin | 006WR00000wk9TCYAY | Other | 2026-04-24 | dormant | — low priority — owner triage when Hold_Reason picklist is enriched.
Brett Spivey | San Clemente | 006WR00000wk9TBYAY | Other | 2026-04-24 | dormant | — low priority — owner triage when Hold_Reason picklist is enriched.
Brett Spivey | Sky at P83 | 006WR00000wk9UVYAY | Other | 2026-04-24 | dormant | — low priority — owner triage when Hold_Reason picklist is enriched.
Brett Spivey | Southwest Patio Home Apartments | 006WR00000wkDu5YAE | Other | 2026-04-24 | dormant | — low priority — owner triage when Hold_Reason picklist is enriched.
Brett Spivey | Stonebridge at Paradise Valley | 006WR00000wk9UTYAY | Other | 2026-04-24 | dormant | — low priority — owner triage when Hold_Reason picklist is enriched.
Brett Spivey | The Cliffs at Canyon Ridge | 006WR00000wkDtsYAE | Other | 2026-04-24 | dormant | — low priority — owner triage when Hold_Reason picklist is enriched.
Brett Spivey | The Enclave at Paradise Valley | 006WR00000wk9UWYAY | Other | 2026-04-24 | dormant | — low priority — owner triage when Hold_Reason picklist is enriched.
Brett Spivey | The M at Lakeline | 006WR00000wkDu1YAE | Other | 2026-04-24 | dormant | — low priority — owner triage when Hold_Reason picklist is enriched.
Brett Spivey | The Towers Apartments | 006WR00000wkArxYAE | Other | 2026-04-24 | dormant | — low priority — owner triage when Hold_Reason picklist is enriched.
Brett Spivey | The Traditions Apartments | 006WR00000wkEbvYAE | Build Not Approved | 2026-04-30 | has signal | — low priority — owner triage when Hold_Reason picklist is enriched.
Brett Spivey | Trillium Apartments | 006WR00000wkDsgYAE | Other | 2026-04-24 | dormant | — low priority — owner triage when Hold_Reason picklist is enriched.
Brett Spivey | Verve | 006WR00000wkAryYAE | Other | 2026-04-24 | dormant | — low priority — owner triage when Hold_Reason picklist is enriched.
Brett Spivey | Wellington Apartments | 006WR00000wkArzYAE | Other | 2026-04-24 | dormant | — low priority — owner triage when Hold_Reason picklist is enriched.
Brett Spivey | Yale Park | 006WR00000wkDtPYAU | Other | 2026-04-24 | dormant | — low priority — owner triage when Hold_Reason picklist is enriched.
Chuck McNeely | 1010 on the Lake | 006WR00000wkEbAYAU | Other | 2026-04-24 | dormant | — low priority — owner triage when Hold_Reason picklist is enriched.
Chuck McNeely | Apache Bend Apartments | 006WR00000wkDMzYAM | Other | 2026-04-24 | dormant | — low priority — owner triage when Hold_Reason picklist is enriched.
Chuck McNeely | Azle Village | 006WR00000wkEbCYAU | Other | 2026-04-24 | dormant | — low priority — owner triage when Hold_Reason picklist is enriched.
Chuck McNeely | Benson Crest | 006WR00000wkEc5YAE | Other | 2026-04-24 | dormant | — low priority — owner triage when Hold_Reason picklist is enriched.
Chuck McNeely | Big Oaks Estates | 006WR00000wkEbEYAU | Other | 2026-04-24 | dormant | — low priority — owner triage when Hold_Reason picklist is enriched.
Chuck McNeely | Boardwalk Caper | 006WR00000wk9UMYAY | Other | 2026-04-24 | dormant | — low priority — owner triage when Hold_Reason picklist is enriched.
Chuck McNeely | Bryce Avenue Apartments | 006WR00000wkClVYAU | Other | 2026-04-24 | dormant | — low priority — owner triage when Hold_Reason picklist is enriched.
Chuck McNeely | Casa Mesa Estates | 006WR00000wkDtpYAE | Other | 2026-04-24 | dormant | — low priority — owner triage when Hold_Reason picklist is enriched.
Chuck McNeely | Cedar Ridge Apartments | 006WR00000wkA9BYAU | Other | 2026-04-24 | dormant | — low priority — owner triage when Hold_Reason picklist is enriched.
Chuck McNeely | Centerpoint Landing | 006WR00000wkBn6YAE | Other | 2026-04-24 | dormant | — low priority — owner triage when Hold_Reason picklist is enriched.
Chuck McNeely | Chalk Hill Ranch Phase 1 | 006WR00000wkEbtYAE | Other | 2026-04-24 | dormant | — low priority — owner triage when Hold_Reason picklist is enriched.
Chuck McNeely | Cimarron Hills | 006WR00000wkDtSYAU | Other | 2026-04-24 | dormant | — low priority — owner triage when Hold_Reason picklist is enriched.
Chuck McNeely | Colonial Plaza | 006WR00000wkDuMYAU | Other | 2026-04-24 | dormant | — low priority — owner triage when Hold_Reason picklist is enriched.
Chuck McNeely | Copper Commons | 006WR00000wkDuQYAU | Other | 2026-04-24 | dormant | — low priority — owner triage when Hold_Reason picklist is enriched.
Chuck McNeely | Country Square | 006WR00000wkBVJYA2 | Other | 2026-04-24 | dormant | — low priority — owner triage when Hold_Reason picklist is enriched.
Chuck McNeely | Cypress View Villas | 006WR00000wkA9HYAU | Other | 2026-04-24 | dormant | — low priority — owner triage when Hold_Reason picklist is enriched.
Chuck McNeely | Dayton Commons | 006WR00000wjnlcYAA | Other | 2026-04-24 | dormant | — low priority — owner triage when Hold_Reason picklist is enriched.
Chuck McNeely | Dixon at Stonegate | 006WR00000wkDMjYAM | Other | 2026-04-24 | dormant | — low priority — owner triage when Hold_Reason picklist is enriched.
Chuck McNeely | Ellipse on Excelsior | 006WR00000wkDtqYAE | Other | 2026-04-24 | dormant | — low priority — owner triage when Hold_Reason picklist is enriched.
Chuck McNeely | Fowler's RV Park | 006WR00000wkDuKYAU | Other | 2026-04-24 | has signal | — low priority — owner triage when Hold_Reason picklist is enriched.
Chuck McNeely | Heatherwilde Park AKA Cove at Heatherwilde | 006WR00000wkEc9YAE | Build Not Approved | 2026-04-24 | dormant | — low priority — owner triage when Hold_Reason picklist is enriched.
Chuck McNeely | Heritage Oaks | 006WR00000wkEbDYAU | Other | 2026-04-24 | dormant | — low priority — owner triage when Hold_Reason picklist is enriched.
Chuck McNeely | Heritage Village Apartments | 006WR00000wkBpDYAU | Other | 2026-04-24 | dormant | — low priority — owner triage when Hold_Reason picklist is enriched.
Chuck McNeely | Holiday Village Manufactured Home Village | 006WR00000wkEbXYAU | Other | 2026-04-24 | dormant | — low priority — owner triage when Hold_Reason picklist is enriched.
Chuck McNeely | Holly Oaks Apartments | 006WR00000wkBp8YAE | Other | 2026-04-24 | dormant | — low priority — owner triage when Hold_Reason picklist is enriched.
Chuck McNeely | Jarrell RV Park | 006WR00000wk9UYYAY | Other | 2026-04-24 | dormant | — low priority — owner triage when Hold_Reason picklist is enriched.
Chuck McNeely | Lakeline Apartments | 006WR00000wkBp7YAE | Other | 2026-04-24 | dormant | — low priority — owner triage when Hold_Reason picklist is enriched.
Chuck McNeely | Lakeside Estates | 006WR00000wkDteYAE | Other | 2026-04-24 | dormant | — low priority — owner triage when Hold_Reason picklist is enriched.
Chuck McNeely | Legend of Fort Worth: Senior Living_OneSource project | 006WR00000wkDttYAE | Other | 2026-04-24 | dormant | — low priority — owner triage when Hold_Reason picklist is enriched.
Chuck McNeely | Live Oak Apartment Homes | 006WR00000wk3P7YAI | Other | 2026-04-24 | dormant | — low priority — owner triage when Hold_Reason picklist is enriched.
Chuck McNeely | Main Street Commons | 006WR00000wkEb4YAE | Other | 2026-04-24 | dormant | — low priority — owner triage when Hold_Reason picklist is enriched.
Chuck McNeely | Oak Creek & Cedar Knob Mobile Home Park | 006WR00000wk9YyYAI | Other | 2026-04-24 | dormant | — low priority — owner triage when Hold_Reason picklist is enriched.
Chuck McNeely | Oaks Apartments | 006WR00000wkBpmYAE | Other | 2026-04-24 | dormant | — low priority — owner triage when Hold_Reason picklist is enriched.
Chuck McNeely | Park View Terrace | 006WR00000wjqCfYAI | Other | 2026-04-24 | dormant | — low priority — owner triage when Hold_Reason picklist is enriched.
Chuck McNeely | Parkside Townhomes | 006WR00000wjnluYAA | Other | 2026-04-24 | dormant | — low priority — owner triage when Hold_Reason picklist is enriched.
Chuck McNeely | Pecan Acres RV Park | 006WR00000wkEb6YAE | Other | 2026-04-24 | has signal | — low priority — owner triage when Hold_Reason picklist is enriched.
Chuck McNeely | Pecan Branch | 006WR00000wk3PJYAY | Other | 2026-04-24 | dormant | — low priority — owner triage when Hold_Reason picklist is enriched.
Chuck McNeely | Reynolds Crossing | 006WR00000wjKGPYA2 | Other | 2026-04-24 | dormant | — low priority — owner triage when Hold_Reason picklist is enriched.
Chuck McNeely | Rio Apartments | 006WR00000wk3PHYAY | Other | 2026-04-24 | dormant | — low priority — owner triage when Hold_Reason picklist is enriched.
Chuck McNeely | SkyView AKA Hoodview Apartments | 006WR00000wkCluYAE | Other | 2026-04-24 | dormant | — low priority — owner triage when Hold_Reason picklist is enriched.
Chuck McNeely | Southcastle Apartments | 006WR00000wkClMYAU | Other | 2026-04-24 | dormant | — low priority — owner triage when Hold_Reason picklist is enriched.
Chuck McNeely | Southern Hills Manufactured Home Community | 006WR00000wkEbFYAU | Other | 2026-04-24 | dormant | — low priority — owner triage when Hold_Reason picklist is enriched.
Chuck McNeely | Stillhouse Flats | 006WR00000wk9Z6YAI | Other | 2026-04-24 | dormant | — low priority — owner triage when Hold_Reason picklist is enriched.
Chuck McNeely | Summer Park _ FF Freddy | 006WR00000wk9StYAI | Other | 2026-04-24 | dormant | — low priority — owner triage when Hold_Reason picklist is enriched.
Chuck McNeely | Sunridge Patio Homes | 006WR00000wkEb3YAE | Other | 2026-04-24 | dormant | — low priority — owner triage when Hold_Reason picklist is enriched.
Chuck McNeely | The Beckham | 006WR00000wkEbBYAU | Other | 2026-04-24 | dormant | — low priority — owner triage when Hold_Reason picklist is enriched.
Chuck McNeely | The Berkeley Apartments | 006WR00000wkDMiYAM | Other | 2026-04-24 | dormant | — low priority — owner triage when Hold_Reason picklist is enriched.
Chuck McNeely | The Bungalows on 204 | 006WR00000wkEb7YAE | Other | 2026-04-24 | dormant | — low priority — owner triage when Hold_Reason picklist is enriched.
Chuck McNeely | The Bungalows on the Lake at Prairie Queen | 006WR00000wkEb8YAE | Other | 2026-04-24 | dormant | — low priority — owner triage when Hold_Reason picklist is enriched.
Chuck McNeely | The Bungalows on the Lake at Prairie Queen_The View | 006WR00000wkEb9YAE | Other | 2026-04-24 | dormant | — low priority — owner triage when Hold_Reason picklist is enriched.
Chuck McNeely | The Canyons Apartments | 006WR00000wkBq5YAE | Other | 2026-04-24 | dormant | — low priority — owner triage when Hold_Reason picklist is enriched.
Chuck McNeely | The Falls & Oaks Village | 006WR00000wkC6VYAU | Other | 2026-04-24 | dormant | — low priority — owner triage when Hold_Reason picklist is enriched.
Chuck McNeely | The Grove at Killeen | 006WR00000wkClGYAU | Other | 2026-04-24 | dormant | — low priority — owner triage when Hold_Reason picklist is enriched.
Chuck McNeely | The Kimberly | 006WR00000wkClsYAE | Other | 2026-04-24 | dormant | — low priority — owner triage when Hold_Reason picklist is enriched.
Chuck McNeely | The Kyle | 006WR00000wkBpPYAU | Other | 2026-04-24 | dormant | — low priority — owner triage when Hold_Reason picklist is enriched.
Chuck McNeely | The Oaks at Liberty Hill Apartments | 006WR00000wkDtTYAU | Other | 2026-04-24 | dormant | — low priority — owner triage when Hold_Reason picklist is enriched.
Chuck McNeely | The Outlook at Windhaven | 006WR00000wkBojYAE | Other | 2026-04-24 | dormant | — low priority — owner triage when Hold_Reason picklist is enriched.
Chuck McNeely | The Summit Brownstones | 006WR00000wk9Z5YAI | Other | 2026-04-24 | dormant | — low priority — owner triage when Hold_Reason picklist is enriched.
Chuck McNeely | The Summit Lofts | 006WR00000wk9TEYAY | Other | 2026-04-24 | dormant | — low priority — owner triage when Hold_Reason picklist is enriched.
Chuck McNeely | The Village of Sun Valley Apartments | 006WR00000wkCl6YAE | Other | 2026-04-24 | dormant | — low priority — owner triage when Hold_Reason picklist is enriched.
Chuck McNeely | Trinity Heights Apartments | 006WR00000wkDMkYAM | Other | 2026-04-24 | dormant | — low priority — owner triage when Hold_Reason picklist is enriched.
Chuck McNeely | Village Creek Townhomes | 006WR00000wk3PGYAY | Other | 2026-04-24 | dormant | — low priority — owner triage when Hold_Reason picklist is enriched.
Chuck McNeely | Waterstone Apartments | 006WR00000wkEbWYAU | Other | 2026-04-24 | dormant | — low priority — owner triage when Hold_Reason picklist is enriched.
Chuck McNeely | Wright Senior | 006WR00000wkEc6YAE | Build Not Approved | 2026-04-24 | dormant | — low priority — owner triage when Hold_Reason picklist is enriched.
Jeff Chao | 502 North | 006WR00000wkCmCYAU | Other | 2026-04-24 | dormant | — low priority — owner triage when Hold_Reason picklist is enriched.
Jeff Chao | Alora Apartments | 006WR00000wkDNVYA2 | Other | 2026-04-24 | dormant | — low priority — owner triage when Hold_Reason picklist is enriched.
Jeff Chao | Alta Cima Apartment Homes | 006WR00000wkDNxYAM | Other | 2026-04-24 | dormant | — low priority — owner triage when Hold_Reason picklist is enriched.
Jeff Chao | Alta Vista | 006WR00000wkDNyYAM | Other | 2026-04-24 | dormant | — low priority — owner triage when Hold_Reason picklist is enriched.
Jeff Chao | Altair | 006WR00000wkDOpYAM | Other | 2026-04-24 | dormant | — low priority — owner triage when Hold_Reason picklist is enriched.
Jeff Chao | Aspire | 006WR00000wkDNzYAM | Other | 2026-04-24 | dormant | — low priority — owner triage when Hold_Reason picklist is enriched.
Jeff Chao | Auburn Glenn | 006WR00000wkDshYAE | Other | 2026-04-24 | dormant | — low priority — owner triage when Hold_Reason picklist is enriched.
Jeff Chao | Avalon Brea Place | 006WR00000wkDNkYAM | Other | 2026-04-24 | dormant | — low priority — owner triage when Hold_Reason picklist is enriched.
Jeff Chao | Avalon Vista X | 006WR00000wkCmEYAU | Other | 2026-04-24 | dormant | — low priority — owner triage when Hold_Reason picklist is enriched.
Jeff Chao | Barham Villas | 006WR00000wkDNWYA2 | Other | 2026-04-24 | dormant | — low priority — owner triage when Hold_Reason picklist is enriched.
Jeff Chao | Benchmark Apartments | 006WR00000wkDOLYA2 | Other | 2026-04-24 | dormant | — low priority — owner triage when Hold_Reason picklist is enriched.
Jeff Chao | Birch Hills Apartments | 006WR00000wkDNlYAM | Other | 2026-04-24 | dormant | — low priority — owner triage when Hold_Reason picklist is enriched.
Jeff Chao | Birchwood Village Apartment Homes | 006WR00000wkDNnYAM | Other | 2026-04-24 | dormant | — low priority — owner triage when Hold_Reason picklist is enriched.
Jeff Chao | Block C at North City | 006WR00000wkDNZYA2 | Other | 2026-04-24 | dormant | — low priority — owner triage when Hold_Reason picklist is enriched.
Jeff Chao | Brea Woods Senior Apartments | 006WR00000wkDOgYAM | Other | 2026-04-24 | dormant | — low priority — owner triage when Hold_Reason picklist is enriched.
Jeff Chao | Bristol Heights | 006WR00000wkCmFYAU | Other | 2026-04-24 | dormant | — low priority — owner triage when Hold_Reason picklist is enriched.
Jeff Chao | Calligraphy | 006WR00000wkDOeYAM | Other | 2026-04-24 | dormant | — low priority — owner triage when Hold_Reason picklist is enriched.
Jeff Chao | Carefree Ranch MHP | 006WR00000wkDNIYA2 | Other | 2026-04-24 | dormant | — low priority — owner triage when Hold_Reason picklist is enriched.
Jeff Chao | Carlton Country Club Villas Apartments | 006WR00000wkDOjYAM | Other | 2026-04-24 | dormant | — low priority — owner triage when Hold_Reason picklist is enriched.
Jeff Chao | Casa De Amigos | 006WR00000wkDNHYA2 | Other | 2026-04-24 | dormant | — low priority — owner triage when Hold_Reason picklist is enriched.
Jeff Chao | Casa Escondida | 006WR00000wkDNJYA2 | Other | 2026-04-24 | dormant | — low priority — owner triage when Hold_Reason picklist is enriched.
Jeff Chao | Casitas Del Sol | 006WR00000wkDNYYA2 | Other | 2026-04-24 | dormant | — low priority — owner triage when Hold_Reason picklist is enriched.
Jeff Chao | Copper Creek Apartment Homes | 006WR00000wkDNXYA2 | Other | 2026-04-24 | dormant | — low priority — owner triage when Hold_Reason picklist is enriched.
Jeff Chao | Coral Tree Manor | 006WR00000wkDOKYA2 | Other | 2026-04-24 | dormant | — low priority — owner triage when Hold_Reason picklist is enriched.
Jeff Chao | Corona Del Vista MHP | 006WR00000wkDNjYAM | Other | 2026-04-24 | dormant | — low priority — owner triage when Hold_Reason picklist is enriched.
Jeff Chao | Country Club Villas ESCONDIDO | 006WR00000wkCjGYAU | Other | 2026-04-24 | dormant | — low priority — owner triage when Hold_Reason picklist is enriched.
Jeff Chao | Country Hills Apartment Homes | 006WR00000wkDOfYAM | Other | 2026-04-24 | dormant | — low priority — owner triage when Hold_Reason picklist is enriched.
Jeff Chao | Country Woods Apartment Homes | 006WR00000wkDNmYAM | Other | 2026-04-24 | dormant | — low priority — owner triage when Hold_Reason picklist is enriched.
Jeff Chao | Courtyard 72 | 006WR00000wkDsJYAU | Other | 2026-04-24 | dormant | — low priority — owner triage when Hold_Reason picklist is enriched.
Jeff Chao | Crest 850 | 006WR00000wkDNAYA2 | Other | 2026-04-24 | dormant | — low priority — owner triage when Hold_Reason picklist is enriched.
Jeff Chao | Crosscreek | 006WR00000wkDNwYAM | Other | 2026-04-24 | dormant | — low priority — owner triage when Hold_Reason picklist is enriched.
Jeff Chao | Eastwood Meadows | 006WR00000wkDP3YAM | Other | 2026-04-24 | dormant | — low priority — owner triage when Hold_Reason picklist is enriched.
Jeff Chao | Eaves San Marcos | 006WR00000wkDOXYA2 | Other | 2026-04-24 | dormant | — low priority — owner triage when Hold_Reason picklist is enriched.
Jeff Chao | Elan Felicita Creek | 006WR00000wkDNSYA2 | Other | 2026-04-24 | dormant | — low priority — owner triage when Hold_Reason picklist is enriched.
Jeff Chao | Elan Northwoods Apartment Homes | 006WR00000wkDOaYAM | Other | 2026-04-24 | dormant | — low priority — owner triage when Hold_Reason picklist is enriched.
Jeff Chao | Elan River Village | 006WR00000wkDN2YAM | Other | 2026-04-24 | dormant | — low priority — owner triage when Hold_Reason picklist is enriched.
Jeff Chao | Escondido Terrace MHP | 006WR00000wkDODYA2 | Other | 2026-04-24 | dormant | — low priority — owner triage when Hold_Reason picklist is enriched.
Jeff Chao | Escondido Village | 006WR00000wkDNUYA2 | Other | 2026-04-24 | dormant | — low priority — owner triage when Hold_Reason picklist is enriched.
Jeff Chao | Estancia Apartments | 006WR00000wkDO4YAM | Other | 2026-04-24 | dormant | — low priority — owner triage when Hold_Reason picklist is enriched.
Jeff Chao | Estrella De Oro | 006WR00000wkDOcYAM | Other | 2026-04-24 | dormant | — low priority — owner triage when Hold_Reason picklist is enriched.
Jeff Chao | Flats on Foothills | 006WR00000wkCmBYAU | Other | 2026-04-24 | dormant | — low priority — owner triage when Hold_Reason picklist is enriched.
Jeff Chao | Forest Glen Apartments | 006WR00000wkDOsYAM | Other | 2026-04-24 | dormant | — low priority — owner triage when Hold_Reason picklist is enriched.
Jeff Chao | Friendly Hills Mobile Manor | 006WR00000wkDNKYA2 | Other | 2026-04-24 | dormant | — low priority — owner triage when Hold_Reason picklist is enriched.
Jeff Chao | Glenbrook Terrace | 006WR00000wkDN3YAM | Other | 2026-04-24 | dormant | — low priority — owner triage when Hold_Reason picklist is enriched.
Jeff Chao | Grandon Village | 006WR00000wkDOPYA2 | Other | 2026-04-24 | dormant | — low priority — owner triage when Hold_Reason picklist is enriched.
Jeff Chao | Greystone Ridge Townhomes | 006WR00000wkDNEYA2 | Other | 2026-04-24 | dormant | — low priority — owner triage when Hold_Reason picklist is enriched.
Jeff Chao | Hadley Apartments | 006WR00000wkDNPYA2 | Other | 2026-04-24 | dormant | — low priority — owner triage when Hold_Reason picklist is enriched.
Jeff Chao | Hendrix Apartments | 006WR00000wkDO0YAM | Other | 2026-04-24 | dormant | — low priority — owner triage when Hold_Reason picklist is enriched.
Jeff Chao | Heritage Park Escondido Senior LIving | 006WR00000wkDP2YAM | Other | 2026-04-24 | dormant | — low priority — owner triage when Hold_Reason picklist is enriched.
Jeff Chao | Heritage Plaza | 006WR00000wkDOhYAM | Other | 2026-04-24 | dormant | — low priority — owner triage when Hold_Reason picklist is enriched.
Jeff Chao | Hidden Cove Apartments | 006WR00000wkDNLYA2 | Other | 2026-04-24 | dormant | — low priority — owner triage when Hold_Reason picklist is enriched.
Jeff Chao | Highland Estates | 006WR00000wkCmDYAU | Other | 2026-04-24 | dormant | — low priority — owner triage when Hold_Reason picklist is enriched.
Jeff Chao | Highlands Mobile Home Park | 006WR00000wkDOnYAM | Other | 2026-04-24 | dormant | — low priority — owner triage when Hold_Reason picklist is enriched.
Jeff Chao | Highline Apartment | 006WR00000wkDNFYA2 | Other | 2026-04-24 | dormant | — low priority — owner triage when Hold_Reason picklist is enriched.
Jeff Chao | Hollydale Mobile Home Estates | 006WR00000wkDNtYAM | Other | 2026-04-24 | dormant | — low priority — owner triage when Hold_Reason picklist is enriched.
Jeff Chao | Imperial Escondido Mobile Estates | 006WR00000wkDP1YAM | Other | 2026-04-24 | dormant | — low priority — owner triage when Hold_Reason picklist is enriched.
Jeff Chao | Indigo at Sunset Park | 006WR00000wkDtrYAE | Other | 2026-04-24 | dormant | — low priority — owner triage when Hold_Reason picklist is enriched.
Jeff Chao | La Mores Estates | 006WR00000wkDOSYA2 | Other | 2026-04-24 | dormant | — low priority — owner triage when Hold_Reason picklist is enriched.
Jeff Chao | La Roca Plaza | 006WR00000wkDNCYA2 | Other | 2026-04-24 | dormant | — low priority — owner triage when Hold_Reason picklist is enriched.
Jeff Chao | Lake Bernardo Mobile Estates | 006WR00000wkDOtYAM | Other | 2026-04-24 | dormant | — low priority — owner triage when Hold_Reason picklist is enriched.
Jeff Chao | Lakeshore Gardens | 006WR00000wkDMfYAM | Other | 2026-04-24 | dormant | — low priority — owner triage when Hold_Reason picklist is enriched.
Jeff Chao | Lantern Crest Senior Living | 006WR00000wkDOkYAM | Other | 2026-04-24 | dormant | — low priority — owner triage when Hold_Reason picklist is enriched.
Jeff Chao | Las Flores Village | 006WR00000wkDOVYA2 | Other | 2026-04-24 | dormant | — low priority — owner triage when Hold_Reason picklist is enriched.
Jeff Chao | Laurel Park | 006WR00000wkDOoYAM | Other | 2026-04-24 | dormant | — low priority — owner triage when Hold_Reason picklist is enriched.
Jeff Chao | Lilac Hills Ranch | 006WR00000wkDOwYAM | Other | 2026-04-24 | dormant | — low priority — owner triage when Hold_Reason picklist is enriched.
Jeff Chao | Madera Ridge | 006WR00000wkDO2YAM | Other | 2026-04-24 | dormant | — low priority — owner triage when Hold_Reason picklist is enriched.
Jeff Chao | Madrid Manor | 006WR00000wkDNfYAM | Other | 2026-04-24 | dormant | — low priority — owner triage when Hold_Reason picklist is enriched.
Jeff Chao | Manzanita Apartments | 006WR00000wkDNNYA2 | Other | 2026-04-24 | dormant | — low priority — owner triage when Hold_Reason picklist is enriched.
Jeff Chao | Mariposa Apartments [Vista | 006WR00000wkACDYA2 | Other | 2026-04-24 | dormant | — low priority — owner triage when Hold_Reason picklist is enriched.
Jeff Chao | Meadow Creek Apartments | 006WR00000wkDNhYAM | Other | 2026-04-24 | dormant | — low priority — owner triage when Hold_Reason picklist is enriched.
Jeff Chao | Meadowbrook | 006WR00000wkDN1YAM | Other | 2026-04-24 | dormant | — low priority — owner triage when Hold_Reason picklist is enriched.
Jeff Chao | Melrose Villa Apartments | 006WR00000wkDOYYA2 | Other | 2026-04-24 | dormant | — low priority — owner triage when Hold_Reason picklist is enriched.
Jeff Chao | Midway Gardens | 006WR00000wkDOJYA2 | Other | 2026-04-24 | dormant | — low priority — owner triage when Hold_Reason picklist is enriched.
Jeff Chao | Mission Gorge Villa | 006WR00000wkDOlYAM | Other | 2026-04-24 | dormant | — low priority — owner triage when Hold_Reason picklist is enriched.
Jeff Chao | Mobile Park West | 006WR00000wkDNQYA2 | Other | 2026-04-24 | dormant | — low priority — owner triage when Hold_Reason picklist is enriched.
Jeff Chao | Oak Hill Apartments | 006WR00000wkDOCYA2 | Other | 2026-04-24 | dormant | — low priority — owner triage when Hold_Reason picklist is enriched.
Jeff Chao | Ocean Park Apartments X | 006WR00000wkClEYAU | Other | 2026-04-24 | dormant | — low priority — owner triage when Hold_Reason picklist is enriched.
Jeff Chao | Overture San Marcos | 006WR00000wkDN6YAM | Other | 2026-04-24 | dormant | — low priority — owner triage when Hold_Reason picklist is enriched.
Jeff Chao | Pacifica Palms Apartments | 006WR00000wkDOIYA2 | Other | 2026-04-24 | dormant | — low priority — owner triage when Hold_Reason picklist is enriched.
Jeff Chao | Palomar Estates | 006WR00000wkDN8YAM | Other | 2026-04-24 | dormant | — low priority — owner triage when Hold_Reason picklist is enriched.
Jeff Chao | Palomar Heights | 006WR00000wkDOzYAM | Other | 2026-04-24 | dormant | — low priority — owner triage when Hold_Reason picklist is enriched.
Jeff Chao | Park | 006WR00000wkDNOYA2 | Other | 2026-04-24 | dormant | — low priority — owner triage when Hold_Reason picklist is enriched.
Jeff Chao | Paseo Del Oro | 006WR00000wkDOOYA2 | Other | 2026-04-24 | dormant | — low priority — owner triage when Hold_Reason picklist is enriched.
Jeff Chao | Ponderosa | 006WR00000wkDNRYA2 | Other | 2026-04-24 | dormant | — low priority — owner triage when Hold_Reason picklist is enriched.
Jeff Chao | Prominence Luxury Apartments | 006WR00000wkDOTYA2 | Other | 2026-04-24 | dormant | — low priority — owner triage when Hold_Reason picklist is enriched.
Jeff Chao | Quail Creek Apartments | 006WR00000wkDN4YAM | Other | 2026-04-24 | dormant | — low priority — owner triage when Hold_Reason picklist is enriched.
Jeff Chao | Raintree Apartment Homes | 006WR00000wkDNrYAM | Other | 2026-04-24 | dormant | — low priority — owner triage when Hold_Reason picklist is enriched.
Jeff Chao | Rancho Brea | 006WR00000wkDNoYAM | Other | 2026-04-24 | dormant | — low priority — owner triage when Hold_Reason picklist is enriched.
Jeff Chao | Rancho Carillo Apartments X | 006WR00000wkClFYAU | Other | 2026-04-24 | dormant | — low priority — owner triage when Hold_Reason picklist is enriched.
Jeff Chao | Rancho Escondido MHP | 006WR00000wkDO1YAM | Other | 2026-04-24 | dormant | — low priority — owner triage when Hold_Reason picklist is enriched.
Jeff Chao | Rancho San Marcos MHP | 006WR00000wkDNiYAM | Other | 2026-04-24 | dormant | — low priority — owner triage when Hold_Reason picklist is enriched.
Jeff Chao | Rancho Santa Fe Village | 006WR00000wkDs6YAE | Other | 2026-04-24 | dormant | — low priority — owner triage when Hold_Reason picklist is enriched.
Jeff Chao | Rancho Vallecitos | 006WR00000wkDOZYA2 | Other | 2026-04-24 | dormant | — low priority — owner triage when Hold_Reason picklist is enriched.
Jeff Chao | Reidy Ceek II | 006WR00000wkDOAYA2 | Other | 2026-04-24 | dormant | — low priority — owner triage when Hold_Reason picklist is enriched.
Jeff Chao | Reidy Creek | 006WR00000wkDOBYA2 | Other | 2026-04-24 | dormant | — low priority — owner triage when Hold_Reason picklist is enriched.
Jeff Chao | Renaissance Villas | 006WR00000wkDObYAM | Other | 2026-04-24 | dormant | — low priority — owner triage when Hold_Reason picklist is enriched.
Jeff Chao | Rowan Apartments | 006WR00000wkDOvYAM | Other | 2026-04-24 | dormant | — low priority — owner triage when Hold_Reason picklist is enriched.
Jeff Chao | Royal Oaks Senior Living | 006WR00000wkDORYA2 | Other | 2026-04-24 | dormant | — low priority — owner triage when Hold_Reason picklist is enriched.
Jeff Chao | Salem Village at Miami Heights | 006WR00000wjnleYAA | Other | 2026-04-24 | dormant | — low priority — owner triage when Hold_Reason picklist is enriched.
Jeff Chao | San Marcos Mobile Estates | 006WR00000wkDNeYAM | Other | 2026-04-24 | dormant | — low priority — owner triage when Hold_Reason picklist is enriched.
Jeff Chao | San Marcos View Estates | 006WR00000wkDNcYAM | Other | 2026-04-24 | dormant | — low priority — owner triage when Hold_Reason picklist is enriched.
Jeff Chao | Santee Corsican Villas | 006WR00000wkDNGYA2 | Other | 2026-04-24 | dormant | — low priority — owner triage when Hold_Reason picklist is enriched.
Jeff Chao | Scott Mountain By the Brook Apartments | 006WR00000wk9UXYAY | Other | 2026-04-24 | dormant | — low priority — owner triage when Hold_Reason picklist is enriched.
Jeff Chao | Sierra Vista | 006WR00000wkDNgYAM | Other | 2026-04-24 | dormant | — low priority — owner triage when Hold_Reason picklist is enriched.
Jeff Chao | Solana at Grand | 006WR00000wkDO7YAM | Other | 2026-04-24 | dormant | — low priority — owner triage when Hold_Reason picklist is enriched.
Jeff Chao | Summer Creek Apartments | 006WR00000wkDOxYAM | Other | 2026-04-24 | dormant | — low priority — owner triage when Hold_Reason picklist is enriched.
Jeff Chao | Summit Apartments | 006WR00000wkDO8YAM | Other | 2026-04-24 | dormant | — low priority — owner triage when Hold_Reason picklist is enriched.
Jeff Chao | Sunset Trails | 006WR00000wkDNBYA2 | Other | 2026-04-24 | dormant | — low priority — owner triage when Hold_Reason picklist is enriched.
Jeff Chao | Tamarack Gardens Apartments | 006WR00000wkDOiYAM | Other | 2026-04-24 | dormant | — low priority — owner triage when Hold_Reason picklist is enriched.
Jeff Chao | Tamarack Woods Apartment Homes | 006WR00000wkDNsYAM | Other | 2026-04-24 | dormant | — low priority — owner triage when Hold_Reason picklist is enriched.
Jeff Chao | Terra Cotta Apartment | 006WR00000wkDN9YAM | Other | 2026-04-24 | dormant | — low priority — owner triage when Hold_Reason picklist is enriched.
Jeff Chao | The Arbors | 006WR00000wkDNvYAM | Other | 2026-04-24 | dormant | — low priority — owner triage when Hold_Reason picklist is enriched.
Jeff Chao | The Avenue at San Marcos | 006WR00000wkDN7YAM | Other | 2026-04-24 | dormant | — low priority — owner triage when Hold_Reason picklist is enriched.
Jeff Chao | The Grand Rose Apartments | 006WR00000wkDOuYAM | Other | 2026-04-24 | dormant | — low priority — owner triage when Hold_Reason picklist is enriched.
Jeff Chao | The Oaks | 006WR00000wkDNuYAM | Other | 2026-04-24 | dormant | — low priority — owner triage when Hold_Reason picklist is enriched.
Jeff Chao | The Springs of Escondido | 006WR00000wkDOHYA2 | Other | 2026-04-24 | dormant | — low priority — owner triage when Hold_Reason picklist is enriched.
Jeff Chao | The Terraces at Escondido | 006WR00000wkDO9YAM | Other | 2026-04-24 | dormant | — low priority — owner triage when Hold_Reason picklist is enriched.
Jeff Chao | The Willows | 006WR00000wkDOrYAM | Other | 2026-04-24 | dormant | — low priority — owner triage when Hold_Reason picklist is enriched.
Jeff Chao | Town Center Apts | 006WR00000wkDOmYAM | Other | 2026-04-24 | dormant | — low priority — owner triage when Hold_Reason picklist is enriched.
Jeff Chao | Town and Country | 006WR00000wkDNpYAM | Other | 2026-04-24 | dormant | — low priority — owner triage when Hold_Reason picklist is enriched.
Jeff Chao | Tuscany Hills | 006WR00000wkDs7YAE | Other | 2026-04-24 | dormant | — low priority — owner triage when Hold_Reason picklist is enriched.
Jeff Chao | Twin Oaks Valley Park | 006WR00000wkDNbYAM | Other | 2026-04-24 | dormant | — low priority — owner triage when Hold_Reason picklist is enriched.
Jeff Chao | Valle Verde Estates | 006WR00000wkDOUYA2 | Other | 2026-04-24 | dormant | — low priority — owner triage when Hold_Reason picklist is enriched.
Jeff Chao | Valle at Escondido | 006WR00000wkDO3YAM | Other | 2026-04-24 | dormant | — low priority — owner triage when Hold_Reason picklist is enriched.
Jeff Chao | Valle at Mission | 006WR00000wkDNMYA2 | Other | 2026-04-24 | dormant | — low priority — owner triage when Hold_Reason picklist is enriched.
Jeff Chao | Valle at Park | 006WR00000wkDO5YAM | Other | 2026-04-24 | dormant | — low priority — owner triage when Hold_Reason picklist is enriched.
Jeff Chao | Valley Parkway MHP | 006WR00000wkDP0YAM | Other | 2026-04-24 | dormant | — low priority — owner triage when Hold_Reason picklist is enriched.
Jeff Chao | Vida | 006WR00000wkDNTYA2 | Other | 2026-04-24 | dormant | — low priority — owner triage when Hold_Reason picklist is enriched.
Jeff Chao | Viewpoint Luxury Apartments | 006WR00000wkDNdYAM | Other | 2026-04-24 | dormant | — low priority — owner triage when Hold_Reason picklist is enriched.
Jeff Chao | Villa Escondido | 006WR00000wkDO6YAM | Other | 2026-04-24 | dormant | — low priority — owner triage when Hold_Reason picklist is enriched.
Jeff Chao | Villa Madeira | 006WR00000wkDOyYAM | Other | 2026-04-24 | dormant | — low priority — owner triage when Hold_Reason picklist is enriched.
Jeff Chao | Villa Serena Apartments | 006WR00000wkDOQYA2 | Other | 2026-04-24 | dormant | — low priority — owner triage when Hold_Reason picklist is enriched.
Jeff Chao | Village Grove Apartments | 006WR00000wkDOFYA2 | Other | 2026-04-24 | dormant | — low priority — owner triage when Hold_Reason picklist is enriched.
Jeff Chao | Vintage Canyon Senior Apartments | 006WR00000wkDNqYAM | Other | 2026-04-24 | dormant | — low priority — owner triage when Hold_Reason picklist is enriched.
Jeff Chao | Vintage Pointe Apartments X | 006WR00000wkClCYAU | Other | 2026-04-24 | dormant | — low priority — owner triage when Hold_Reason picklist is enriched.
Jeff Chao | Vintage Pointe II X | 006WR00000wkClDYAU | Other | 2026-04-24 | dormant | — low priority — owner triage when Hold_Reason picklist is enriched.
Jeff Chao | Vista Blue | 006WR00000wkDMdYAM | Other | 2026-04-24 | dormant | — low priority — owner triage when Hold_Reason picklist is enriched.
Jeff Chao | Waterleaf Apartment Homes | 006WR00000wkDOdYAM | Other | 2026-04-24 | dormant | — low priority — owner triage when Hold_Reason picklist is enriched.
Jeff Chao | Westlake Village | 006WR00000wkDNaYAM | Other | 2026-04-24 | dormant | — low priority — owner triage when Hold_Reason picklist is enriched.
Jeff Chao | Westmont Town Court | 006WR00000wkDOGYA2 | Other | 2026-04-24 | dormant | — low priority — owner triage when Hold_Reason picklist is enriched.
Jeff Chao | Westwinds MHP | 006WR00000wkDOEYA2 | Other | 2026-04-24 | dormant | — low priority — owner triage when Hold_Reason picklist is enriched.
Jeff Chao | Widsor Manor II | 006WR00000wkDOWYA2 | Other | 2026-04-24 | dormant | — low priority — owner triage when Hold_Reason picklist is enriched.
Jeff Chao | Windsor Gardens | 006WR00000wkDN5YAM | Other | 2026-04-24 | dormant | — low priority — owner triage when Hold_Reason picklist is enriched.
Jeff Chao | Windsor Manor I | 006WR00000wkDONYA2 | Other | 2026-04-24 | dormant | — low priority — owner triage when Hold_Reason picklist is enriched.
Jeff Chao | Woodbine Apartments | 006WR00000wkCl4YAE | Other | 2026-04-24 | dormant | — low priority — owner triage when Hold_Reason picklist is enriched.
Jeff Chao | Woodglen Vista Apartments | 006WR00000wkDNDYA2 | Other | 2026-04-24 | dormant | — low priority — owner triage when Hold_Reason picklist is enriched.
Jeff Chao | Woodlake Apartments | 006WR00000wkDOqYAM | Other | 2026-04-24 | dormant | — low priority — owner triage when Hold_Reason picklist is enriched.
Jeff Chao | Woodland Village | 006WR00000wkDOMYA2 | Other | 2026-04-24 | dormant | — low priority — owner triage when Hold_Reason picklist is enriched.
Jeff Wickersham | Fellowship Square Historic Mesa | 006WR00000wkC6yYAE | Other | 2026-04-24 | dormant | — low priority — owner triage when Hold_Reason picklist is enriched.
Jeff Wickersham | Greenfield Village RV Resort | 006WR00000wkEb5YAE | Other | 2026-04-24 | dormant | — low priority — owner triage when Hold_Reason picklist is enriched.
Jeff Wickersham | Mesa Spirit RV Resort | 006WR00000wkDsiYAE | Other | 2026-04-24 | dormant | — low priority — owner triage when Hold_Reason picklist is enriched.
Jeff Wickersham | Primrose Estates | 006WR00000wkAqzYAE | Other | 2026-04-24 | dormant | — low priority — owner triage when Hold_Reason picklist is enriched.
Jeff Wickersham | Wintercove Park | 006WR00000wjnlYYAQ | Other | 2026-04-24 | dormant | — low priority — owner triage when Hold_Reason picklist is enriched.
Justin Barry | Monte Mira HOA | 006WR00000yvoqPYAQ | Budget / Timing | 2026-05-01 | has signal | — low priority — owner triage when Hold_Reason picklist is enriched.
Justin Barry | Park Encinitas | 006WR00000wkCmJYAU | Other | 2026-04-24 | dormant | — low priority — owner triage when Hold_Reason picklist is enriched.
Marty Samuels | Aspire Mesa | 006WR00000wkDsfYAE | Other | 2026-04-24 | dormant | — low priority — owner triage when Hold_Reason picklist is enriched.
Marty Samuels | Avenue 8 Apartments | 006WR00000wkDuCYAU | Other | 2026-04-24 | dormant | — low priority — owner triage when Hold_Reason picklist is enriched.
Marty Samuels | Brookwood Apartments | 006WR00000wkDuEYAU | Other | 2026-04-24 | dormant | — low priority — owner triage when Hold_Reason picklist is enriched.
Marty Samuels | Cambria Apartments | 006WR00000wkDtyYAE | Other | 2026-04-24 | dormant | — low priority — owner triage when Hold_Reason picklist is enriched.
Marty Samuels | Comanche Wells | 006WR00000wkEZqYAM | Other | 2026-04-24 | dormant | — low priority — owner triage when Hold_Reason picklist is enriched.
Marty Samuels | Craft at Gilbert and Baseline | 006WR00000wkCmGYAU | Other | 2026-04-24 | dormant | — low priority — owner triage when Hold_Reason picklist is enriched.
Marty Samuels | HUE97 | 006WR00000wkClKYAU | Other | 2026-04-24 | dormant | — low priority — owner triage when Hold_Reason picklist is enriched.
Marty Samuels | Mission Palms Apartments | 006WR00000wkDuGYAU | Other | 2026-04-24 | dormant | — low priority — owner triage when Hold_Reason picklist is enriched.
Marty Samuels | River Oaks Apartments | 006WR00000wkDuHYAU | Other | 2026-04-24 | dormant | — low priority — owner triage when Hold_Reason picklist is enriched.
Marty Samuels | Riverview Townhomes | 006WR00000wkDuBYAU | Other | 2026-04-24 | dormant | — low priority — owner triage when Hold_Reason picklist is enriched.
Marty Samuels | San Jose Manor Apts | 006WR00000wk9U9YAI | Other | 2026-04-24 | dormant | — low priority — owner triage when Hold_Reason picklist is enriched.
Marty Samuels | San Miguel Apartments | 006WR00000wk9TGYAY | Other | 2026-04-24 | dormant | — low priority — owner triage when Hold_Reason picklist is enriched.
Marty Samuels | San Montego Luxury Apartments | 006WR00000wkDu7YAE | Other | 2026-04-24 | dormant | — low priority — owner triage when Hold_Reason picklist is enriched.
Marty Samuels | SunVilla Apartments | 006WR00000wj8JaYAI | Other | 2026-04-24 | dormant | — low priority — owner triage when Hold_Reason picklist is enriched.
Marty Samuels | The Turn Apartments | 006WR00000wkDu8YAE | Other | 2026-04-24 | dormant | — low priority — owner triage when Hold_Reason picklist is enriched.
Marty Samuels | Tierra Pointe | 006WR00000wkEZoYAM | Other | 2026-04-24 | dormant | — low priority — owner triage when Hold_Reason picklist is enriched.
Marty Samuels | Zona Village | 006WR00000wkDuIYAU | Other | 2026-04-24 | dormant | — low priority — owner triage when Hold_Reason picklist is enriched.
Melissa Baker | 120 Sunset Dr | 006WR00000wk9RvYAI | Other | 2026-04-24 | dormant | — low priority — owner triage when Hold_Reason picklist is enriched.
Melissa Baker | 424 Avenida Granada | 006WR00000wk9RwYAI | Other | 2026-04-24 | dormant | — low priority — owner triage when Hold_Reason picklist is enriched.
Melissa Baker | Horizon Heights | 006WR00000wkEb1YAE | Other | 2026-04-29 | has signal | — low priority — owner triage when Hold_Reason picklist is enriched.
Taylor Mauney | TEST PROPERTY 2 | 006WR0000112YsXYAU | Ownership Change | 2026-04-22 | has signal | — low priority — owner triage when Hold_Reason picklist is enriched.